## Sheet1
Concurrent Activties from the receipt of Stock Position to release of PO
BIDDERS | PREPARATION AND SIGNING OF BAC RESOLUTION, NOA PREPARATION | APPROVAL OF BAC RESOLUTION AND NOA | DATE OF NOA EMAILED TO BIDDER | DATE ACKNOWLEDGED BY BIDDER | DATE OF PERFORMANCE SECURITY DEALINE (10 DAYS FROM RECEIPT OF NOA) | DATE OF ENDORSEMENT OF COPY OF NOA TO PHARMACY | STOCK POSITION RECEIVED | STOCK POSITION # OF ITEMS | DATE ENDORSED TO BUDGET | Date Returned by Accounting | Reason for Return | Date Endorsed to Accounting | Date Returned by Accounting 2 | Reason for Return 2 | Date Endorsed to Accounting 2 | REMARKS | Procurement Activities (Project ID) | Date Started | Column 13
2MG INCORPORATED | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-13 | 2026-07-17 | 2026-07-22 | 10 | 2026-08-08 | 2026-08-18 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK, NO OSS | [5 empty] | DBE (G37A) | 2026-07-22 | 2026-07-24
BANSAN PHARMA | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-22 | 3 | 2026-07-27 | 2026-07-30 | No OSS and last page PR. BAC Chair signature on the sealed bids, and check page 14 of BAC RESO Bansan Post-Disqualified | 2026-08-03 |  |  |  |  | PE (G39A) | 2026-07-23
BIOLOGIC LIFE | 2026-06-24 | 2026-07-01 | 2026-07-03 | 2026-07-09 | 2026-07-19 | 2026-07-17 | 2026-07-22 | 1 | 2026-07-27 | 7/ 30/2026 | NO OSS attached and last Page PR. | 2026-08-03 |  |  |  |  | DBE (G39A) | 2026-07-24 | 2026-07-27
DELEX PHARMA | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-22 | 4 | 2026-07-24 | 2026-07-30 | NO OSS attached and last Page PR. | 2026-08-03 |  |  |  |  | PQE (G35A) | 2026-07-28 | 2026-07-30
GENACE PHARMA | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-05 | 2026-07-15 | 2026-07-17 | 2026-07-22 | 7 | 2026-07-30 | 2026-08-10 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK | 08/12/0226 |  |  |  |  | PQE (G36A) | 2026-07-28 | 2026-07-30
GETZ BRO | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-17 | 2026-07-17 | 2026-07-22 | 1 | 2026-07-30 | 2026-08-05 | Amount in NTP does not match in PO, No OSS | 2026-08-06 | 08/14/0226 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK | 2026-08-18 |  | PQE (G38A) | 2026-07-28 | 2026-07-30
GLOBO ASIATICO | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-14 | 2026-07-24 | 2026-07-17 | 2026-07-22 | 4 | 2026-07-30 | 2026-08-10 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK | 2026-08-12 |  |  |  |  | BAC Meeting | 2026-07-29
IDS MEDICAL SYSTEMS | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-07 | 2026-07-17 | 2026-07-17 | 2026-07-22 | 1 | 2026-07-30 | 2026-08-10 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK, and no OSS | 2026-08-12 |  |  |  |  | BAC Meeting | 2026-07-30
JOSMEF ENTERPRISES | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-22 | 2 | 2026-07-27 | 2026-07-30 | No OSS and last page PR. BAC Chair signature on the sealed bids, and check page 14 of BAC RESO Bansan Post-Disqualified | 2026-08-03 |  |  |  |  | PQE (G39A) | 2026-07-31
ONICARE | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-22 | 1 | [7 empty] | CANCELLED | BAC Meeting | 2026-08-03
OXFORD | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-08 | 2026-07-18 | 2026-07-17 | 2026-07-22 | 17 | 2026-08-06 | 2026-08-18 | check page 7 BAC Reso for GETSZ BROS AND SAVELINK | 2026-08-18 |  |  |  |  | PQE (G37A) | 2026-08-06 | 2026-08-10
SANDOVAL | 2026-06-24 | 2026-07-01 | 2026-07-02 | 8446783 | 8446793 | 2026-07-17 | 2026-07-22 | 4 | 2026-08-04 | 2026-08-07 | Sealed bids and No OSS attached | 2026-08-11 |  |  |  |  | BAC Meeting | 2026-08-07
UNILAB | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-22 | 2 | 2026-08-03 | [7 empty] | BAC Meeting | 2026-08-11
VIZCARRA | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-04 | 2026-07-14 | 2026-07-17 | 2026-07-22 | 2 | 2026-07-27 | 2026-07-30 | No OSS and last page PR. BAC Chair signature on the sealed bids, and check page 14 of BAC RESO Bansan Post-Disqualified | 2026-08-03
SAVELINK | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-23 | 92 | 2026-07-28 | 2026-08-10 | Stock position and delivery sched. and check page 7 and 13 BAC reso | 2026-08-12
DYNASTY | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-02 | 2026-07-12 | 2026-07-17 | 2026-07-23 | 27 | 2026-08-11 | 2026-08-14 | no OSS attached, correct brand name, Oxytocin not in the PR. | 2026-08-17
ZUELLIG | 2026-06-24 | 2026-07-01 | 2026-07-02 | 2026-07-13 | 2026-07-23 | 2026-07-17 | 2026-07-23 | 69
PHILPHARMAWEALTH | 2026-06-24: 2026-06-24; 2026-07-01: 2026-07-01; 2026-07-02: 2026-07-02; 2026-07-17: 2026-07-17 | 76
SANNOVEX | 2026-06-24 | 2026-07-01 | 2026-08-05 | 2026-08-05 | 2026-08-15 |  |  | 7
Procurement Activities | Dated Started | Date Ended | Duration | Allowable Duration (days) | Remarks
Date of Receipt of PR | 2026-06-24: 2026-03-26
Date of Pre-procurement | 2026-06-24: 2026-03-31; 2026-07-04: 1
Date of Final Meeting on Mearb Criteria | 2026-06-24: 2026-04-06
Date of Posting | 2026-06-24: 2026-04-07; 2026-07-02: 7 days; 2026-07-04: 7
Date of Opening of Bids | 2026-06-24: 2026-04-28; 2026-07-02: 1 day; 2026-07-04: 1
Date of Bid Evaluation | 2026-06-24: 2026-04-29; 2026-07-01: 2026-05-12; 2026-07-04: 7
Date of Posqualification | 2026-06-24: 2026-05-13; 2026-07-01: 2026-06-24; 2026-07-02: Approved Extension: 45 cd (July 27, 2026); 2026-07-04: 12 to 45 from determination of LCB/MEAB/MAB after Detailed Evaluation